## Slide 1: Navigating HHEAR Post-Approval
Phase 1: Clearance Activities
Notes: Welcome to the module “Navigating HHEAR Post-Approval” … phase 1… Clearance Activities

## Slide 2: Navigating HHEAR Post-Approval (1 of 2)
The Steps of the Post-Approval process include:
This module will focus on this step
Notes: As reviewed in the Post-Approval Overview, there are four main phases of the Post-Approval process. In this module we will dig into the details of the first phase: Clearance Activities.

## Slide 3: Navigating HHEAR Post-Approval (2 of 2)
Objectives:
Understand the steps to obtain HHEAR services following the approval of your HHEAR application: The Post-Approval Process.
Be aware of critical deadlines for submitting required documents and data in the “Clearance Activities” stage.
Obtain access to guidance and tools for successfully navigating the post-approval process.
Notes: The objectives for today are as follows:
Understand the steps to obtain HHEAR services following the approval of your HHEAR application: The Post-Approval Process.
Be aware of critical deadlines for submitting required documents and data in the “Clearance Activity” stage.
Obtain access to guidance and tools for successfully navigating the post-approval process.
… let’s get started…

## Slide 4: Clearance Activities (1 of 2)
Notes: You may recall this flow chart from the Post-Approval Process overview. We will anchor back to this through out the module...
BUT FIRST….

## Slide 5: Clearance Activities – first steps after approval (1 of 2)
Immediately upon approval, you will need to take the following action:
  Review any required or optional modifications to your application, per the review committee.
  Send written agreement to HHEAR_CC@westat.com.
Tip
Reach out to the HHEAR Coordinating Center at HHEAR_CC@westat.com if you have any difficulties during the clearance activities stage!
Notes: IMMEDIATELY upon approval, the HHEAR Coordinating Center will notify you of any required or optional modifications to your application that came from the review committee. It is critical that you promptly review and agree to these modifications. Written agreement should be sent to HHEAR_CC@westat.com.
If you have questions or concerns regarding these modifications, contact the HHEAR Coordinating Center at HHEAR_CC@westat.com right away.
Once any modifications are addressed, the clearance activities phase begins..

## Slide 6: Clearance Activities (2 of 2)
Notes: The HHEAR CC will contact you after your project is approved and modifications are made to complete several activities. They will provide you with a link to MyHHEAR forms where signed documents and assurances need to be uploaded. All of these activities must be completed before you can ship your samples to a Lab Hub for analysis.
The first activities, the IRB Attestation Letter, Signing the Data Submission Agreement, and Signing the Data Sharing Plan should be completed in 8 weeks. Additionally, the Human and/or Environmental Materials Transfer Agreement for each lab hub you will be working with should be completed within 10-12 weeks of approval…. And a laboratory analysis plan should be completed for each approved analysis within 12 weeks after approval. We will talk more in-depth about each of these in the next few slides.
The flow chart also highlights the steps following the IRB Attestation Letter and DSA & DSP… Note the DC will approve these documents, and THEN the PI will submit project data, which will then be approved by the DC – this is the last step of the clearance activities phase. All of this takes place within 12-16 weeks post approval.

## Slide 7: Clearance Activities – first steps after approval (2 of 2)
Tips
Start all clearance activities as soon as you receive notification that your project is approved.
Work on all clearance activities simultaneously.
Stick to the timeline.
Warning: projects with excessive delays cannot be guaranteed HHEAR services.
Notes: Here are a few general, but critical, tips to keep in mind for this stage of your project:
First, start all clearance activities as soon as you receive notification that your project is approved. It may seem like the deadlines are far away, but unexpected delays can arise… so to ensure they don’t impact your ability to meet deadlines, you must begin work on these activities immediately.
Second, work on the clearance activities simultaneously. There is no need to wait until one part is done to complete another… again, you never know what could cause a delay, so it is best to begin right away.
Third, stick to the timeline. It is important that to the best of your ability, you stick to the timeline. There are procedures in place to apply for extensions when absolutely necessary, however it is critical that you understand that projects with excessive delays run the risk of not being analyzed. Projects enter the lab queue as the samples arrive at the lab, so when projects are delayed, they fall further in the lab queue.

## Slide 8: Clearance Activities - 8 weeks post-approval (1 of 4)
IRB Attestation Letter
Letter from your IRB stating that:
  the original study consent permits the use of samples and data for your HHEAR project; and
  data submission and subsequent data sharing for future unspecified research purposes are consistent with the informed consent utilized with study participants.
This is not a new IRB approval
An example/template can be found on the website, and is also linked here (Example Attestation letter).
Notes: Now that we’ve discussed the overall process, Let’s dive into the details…
The IRB attestation letter. This is a letter from your IRB – it is not a new IRB approval. This letter must state that the original study consents permit the use of samples and data for your HHEAR project. It also must verify that the data submission and subsequent data-sharing for future unspecified research purposes are consistent with the informed consent that was utilized with the study’s participants. You may recall, in earlier modules we mentioned that the ability to submit and share data is a critical component to receiving HHEAR services. Because of this, informed consent consistent with the use of data for future UNSPECIFIED research purposes is absolutely critical.
A template letter can be found on the HHEAR website and is linked in this slide. Note that all active links in this module (and all other modules) are available in the PowerPoint that is provided on the HHEAR website.

## Slide 9: Clearance Activities - 8 weeks post-approval (2 of 4)
Tips
Be sure to complete this step promptly as it requires approval before receiving access to the HHEAR Data Center Portal!
The IRB Attestation Letter must apply to all samples and data that you will use to achieve your study aims. Projects that include multiple cohorts with separate IRBs may require multiple IRB Attestation Letters.
Since sharing your data through the HHEAR Data Center Portal is a requirement of HHEAR, and the IRB Attestation Letter is a requirement to obtain access to the portal, your project will be stopped if you can not provide the required IRB attestation letter.
Notes: Please note the tip on this screen. You will want to be sure to submit your IRB attestation letter promptly, as it is required before receiving access to the HHEAR Data Center Portal! This is critical for subsequent steps in the process including the upload of your data to the data center.
The IRB Attestation Letter must apply to all samples and data that you will use to achieve your study aims. Projects that include multiple cohorts with separate IRBs may require multiple IRB Attestation Letters.
Your project will be stopped if you are unable to provide the required IRB attestation letter.
The IRB Attestation Letter can be submitted by uploading it to myHHEAR through your myHHEAR account.

## Slide 10: Clearance Activities - 8 weeks post-approval (3 of 4)
Signed & Submitted
Data Submission Agreement:
DSA
Outlines your agreement with HHEAR regarding the submission of data to the HHEAR Data Repository.
HHEAR Data Repository Data Submission Agreement
Data Sharing Plan:
DSP
Describes data types, data repositories to which data will be submitted, the timeline for data submission and release, and the appropriate uses of data.
Data Sharing Plan for the HHEAR Data Repository
Tip
Be sure to complete this step promptly as it is required before receiving access to the HHEAR Data Center Portal!
Notes: The next items that require your attention post-approval relate to data sharing!
Within 8-weeks of being approved you will need to submit a signed Data Submission Agreement (or DSA) and a signed Data Sharing Plan (or DSP).
The Data Submission AGREEMENT outlines your agreement with HHEAR regarding the submission of data to the HHEAR data Repository.
The Data Sharing PLAN describes the data types included, the data repositories to which data will be submitted, the timeline for data submission and release…. And … the appropriate uses of data.
Note there are links to each of these items on this slide AND they can be found on the HHEAR website.
The DSA and DSP can be submitted by uploading each to myHHEAR through your myHHEAR account.
Also… Please note the tip on this slide is the same as for the IRB attestation letter… You will receive access to the HHEAR Data Center Portal only after the IRB Attestation Letter, DSA, and DSP are both submitted and approved.

## Slide 11: Clearance Activities - 8 weeks post-approval (4 of 4)
REMEMBER:
Submit the signed DSA, DSP, and IRB Attestation Letter by uploading the appropriate form in myHHEAR no later than 8 weeks after your project is approved
These forms will be reviewed by the HHEAR Data Center within 1 week of document submission.
Once approved, the Data Center will contact you with instructions for how to access and log in to the HHEAR Data Center Portal to upload your project epidemiological data.
Notes: Submitting signed Data Submission Agreements, Data Sharing Plans, and the IRB Attestation Letter is critical to your project moving forward. Once these items are uploaded to myHHEAR, the forms will be reviewed by the HHEAR data center. Once the Data Center has approved the documents, you will be contacted with instruction for accessing the Data Center Portal and how to upload your project’s epidemiological data… your data must be uploaded no later than 12 weeks post approval.

## Slide 12: Clearance Activities - 12 weeks post-approval (1 of 7)
Material Transfer Agreements
“A Material Transfer Agreement (MTA) is a contract that governs the transfer of tangible research materials between two organizations, when the recipient intends to use it for his or her own research purposes. An MTA defines the rights of the provider and the recipient with respect to the materials and any derivatives.”
2 types:
  Human Materials Transfer Agreement (H-MTA)
  Environmental Materials Transfer Agreement (E-MTA)
These documents are used to facilitate the transfer of human biological materials and/or environmental samples between the PI and a HHEAR Lab Hub.
H-MTA
E-MTA
Notes: By the 12-weeks post-approval the relevant Material Transfer Agreements must be completed and submitted to the Coordinating Center. Note this is with OR without accompanying data.
“A Material Transfer Agreement (MTA) is a contract that governs the transfer of tangible research materials between two organizations, when the recipient intends to use it for his or her own research purposes. An MTA defines the rights of the provider and the recipient with respect to the materials and any derivatives.”
There are 2 types of MTAs:
  Human Materials Transfer Agreement (H-MTA)
  Environmental Materials Transfer Agreement (E-MTA)
Both of these forms are linked in this slide AND can be found on the website.
These documents are used to facilitate the transfer of human biological materials and/or environmental samples between the PI and a HHEAR Lab Hub.

## Slide 13: Clearance Activities - 12 weeks post-approval (2 of 7)
Tips
An MTA is needed for each HHEAR Lab Hub that will be receiving samples from you.
  Transfer of samples between HHEAR Lab Hubs is covered by the HHEAR Material Collaboration Agreement.
Please note that substantial changes to these documents can result in delays in the process, so you will want to begin work on these immediately upon approval notification.
If you have questions regarding these documents, please reach out to the Coordinating Center at HHEAR_CC@westat.com
Notes: An MTA is needed for each HHEAR Lab Hub that will be receiving materials from you, the PI.
  Transfer of samples between HHEAR Lab Hubs is covered by the HHEAR Material Collaboration Agreement.
Please note that substantial changes to these documents can result in delays in the process, so you will want to begin work on these immediately upon approval notification.
If you have questions regarding these documents, please reach out to the Coordinating Center at HHEAR_CC@westat.com

## Slide 14: Clearance Activities - 12 weeks post-approval (3 of 7)
Develop a Lab Analysis Plan (LAP)
Work with the Lab Hub(s) to create a DETAILED LAP.
This is a critical step as it outlines what samples are needed and the analyses that are to be done.
Once the Data Center approves the IRB attestation letter, DSA, and DSP, the Data Center will contact you to upload your project epi data to the Data Center Portal.
You will want to work closely with your Lab Hub during this process as they may have additional lab-specific needs (such as a detailed statements of work) depending on your project details and the Lab Hubs specific processes.
Notes: Within 12 weeks after your application is approved:
You will need to complete a detailed lab analysis plan or plans in coordination with the Lab Hubs assigned to your project. Please note that this process should begin promptly after your approval notification. You will need to work on this simultaneously with the items that have the 8-week deadline… you just have an additional 4 weeks to complete the LAP.
Work with the Lab Hub(s) to create a DETAILED LAP.
This is a critical step as it outlines what samples are needed and the analyses that are to be done.
Once the Data Center approves the IRB attestation letter, DSA, and DSP, the Data Center will contact you to upload your project epi data to the Data Center Portal.
You will want to work closely with your Lab Hub during this process as they may have additional lab-specific needs (such as a detailed statements of work) depending on your project details and the Lab Hubs specific processes.

## Slide 15: Clearance Activities - 12 weeks post-approval (4 of 7)
Components of the Laboratory Analysis Plan
Details about number and type of samples to be analyzed
Names of analytes
Analyte adjustment factors
QC Plan
Randomization
Sample aliquoting
Labeling and shipment
Associated sample or participant data
Projected timelines
Documentation of Publications Policy agreement
Notes: Components of the Laboratory Analysis Plan include:
Details about number and type of samples to be analyzed
Names of analytes
Analyte adjustment factors
QC Plan
Randomization
Sample aliquoting
Labeling and shipment
Associated sample or participant data
Projected timelines
Documentation of Publications Policy agreement

## Slide 16: Clearance Activities - 12 weeks post-approval (5 of 7)
PLEASE NOTE:
  A pre-test of samples may be included as a part of the lab analysis plan.
    The purpose of a pre-test is to establish the feasibility of the sample analysis or fitness of the samples.
    Not all studies will need a pre-test.
Tip
More information on how to conduct a pre-test is provided in Appendix 2 of HHEAR’s Policies for Access to Services on our website, also linked here (HHEAR Policies for Access to Services).
Notes: PLEASE NOTE:
Your plan may include a pre-test of samples to confirm their fitness for the requested analyses.
The purpose of a pre-test is to establish the feasibility of the sample analysis or fitness of the samples.
Not all studies will need a pre-test.
Note that More information on how to conduct a pre-test is provided in Appendix 2 of HHEAR’s Policies for Access to Services on our website, also linked here.

## Slide 17: Clearance Activities - 12 weeks post-approval (6 of 7)
Upload epidemiological data from the parent study to the HHEAR Data Center Portal
You will receive access to the Data Center Portal after the IRB Attestation Letter, DSA, and DSP are submitted and approved.
The DC will tell you what data to include and how to upload files.
The DC will review the project data; the PI should be prepared to respond to questions about the data.
The PI will link Participant IDs (PIDs) to original study data inside the Data Portal.
NOTE: The Data Center must approve your project data BEFORE you ship samples to the Lab Hub.
Notes: You will receive access to the Data Center Portal after the IRB Attestation Letter, DSA, and DSP are submitted and approved.
At this point you will upload epidemiological data from your parent study to the HHEAR Data Center Portal.
The Data Center tells you what data to include and how to upload your data files.
The Data Center must approve your data before you can ship samples to the Lab Hub(s).
You will need to link your PIDs to the original study data.
Please note again that The Data Center must approve your project data BEFORE you may ship samples to the Lab Hub.

## Slide 18: Clearance Activities - 12 weeks post-approval (7 of 7)
Transfer Sample-level data files to Lab Hub(s), if needed.
  This may include sample characteristics and/or phenotypic data
    Collection method, duration of storage, participant age, etc.
  The Lab Hub(s) will work directly with the PI to coordinate this step.
    Please note that this step is not tracked in myHHEAR.
Notes: For some studies, sample-level data files will also need to be sent to the Lab Hub or hubs working with your project. This will not apply to all studies.
  This may include sample characteristics and/or phenotypic data
    For example, for quality control or analysis, the lab might require information related to collection method, duration of storage, participant age, or other similar data.
  The Lab Hub or hubs will work directly with the PI to coordinate this step.
    Please note that this step is not tracked in myHHEAR.

## Slide 19: Clearance Activities - Tips
Tips
Be sure to complete the IRB attestation letter, DSA, and DSP promptly as all must be submitted and approved before receiving access to the HHEAR Data Center Portal!
All clearance activities, including submitting project data to the Data Center MUST be completed before samples can be shipped to Lab Hubs.
Reach out to the HHEAR Coordinating Center at HHEAR_CC@westat.com if you have any difficulties during the clearance activities stage!
As you prepare for the next stage, we recommend that you reach out to your assigned lab hub to ensure your samples are stored/prepared in a manner appropriate for the planned analyses.
If there is any deviation in the available samples relative to the approved plan (i.e., a reduction in the number of samples), contact the HHEAR Coordinating Center at HHEAR_CC@westat.com right away.
Notes: Just as a reminder… here are a few important tips for this section
Be sure to complete the IRB attestation letter, DSA, and DSP promptly as all must be submitted and approved before receiving access to the HHEAR Data Center Portal!
All clearance activities, including submitting project data to the Data Center MUST be completed before samples can be shipped to Lab Hubs.
Reach out to the HHEAR coordinating center at HHEAR_CC@westat.com if you have any difficulties during the clearance activity stage!
As you prepare for the next stage, we recommend that you reach out to your assigned lab hub to ensure your samples are stored/prepared in a manner appropriate for the planned analyses.
If there is any deviation in the available samples relative to the approved plan (i.e., a reduction in the number of samples), contact the HHEAR Coordinating Center at HHEAR_CC@westat.com right away.

## Slide 20: Reminders
Start all clearance activities immediately
Excessive delays or missing documents can jeopardize access to services
If you have questions or concerns, reach out to the HHEAR Coordinating Center at HHEAR_CC@westat.com.
Notes: There are components due at 8-weeks post approval and components due at 12 weeks post approval. It is of the utmost importance that you stick to the deadlines to ensure access to services.
You will want to start all clearance activities immediately – this helps mitigate the impacts of unexpected delays.
Pease remember that excessive delays or missing documents can jeopardize access to services
If you have questions or concerns, please remember that you can always reach out to the HHEAR Coordinating Center at HHEAR_CC@westat.com for assistance!

## Slide 21: Resources
Refer to the following webpages for more information:
  How to Apply
    https://hhearprogram.org/how-apply
  Policies
    https://hhearprogram.org/policies
  Support Documents
    https://hhearprogram.org/support-docs
  FAQs
    https://hhearprogram.org/faqs
  Data Center Portal & Data Repository
    https://hheardatacenter.mssm.edu
Notes: As a reminder there is additional information available on the HHEAR website such as How to Apply, Policies, Support Documents, FAQs, and links to the data center portal or data repository… each of which is also linked on this slide.
Good luck and remember we are here to help!